## Projekt
Project Schedule
V1.0
User Identification in an interactive room using Kinect | [20 empty] | Legend | [9 empty] | Legend
Current work week |  |  |  | 1
Student: |  |  |  | Matthias Bloch | [18 empty] | Deadline |  |  | Progress (current) |  |  |  | Vacation |  | Deadline |  | Progress (current) | Vacation
Supervisor: |  |  |  | Ali Alavi | [18 empty] | Presentation |  |  | Progress (delayed) |  |  |  | Work days |  | Presentation |  | Progress (delayed) | Work days
Thesis Start (registration pending): |  | 2016-10-17
Thesis End: |  | 2017-04-17
Presentations | [5 empty] | Project Deadlines | [7 empty] | Workload Definition | [7 empty] | Vacation/Misc
Presentation |  | Date |  |  |  | Milestone |  |  |  |  | Deadline |  |  | Approximated Workload
Intermediate Defense |  | end of december |  |  |  | Kinect SDK setup |  |  |  |  | WK 1 |  |  | Total workload |  |  |  |  | 900 | h |  | Vacation |  |  |  |  | 1 day |  | 2016-10-28
Final Defense |  | april/may |  |  |  | First prototype |  |  |  |  | WK 9 |  |  | Weekly workload |  |  |  |  | 42 | h |  | Christmas holidays |  |  |  |  | 7 days |  | 24.12.16-03.1.17
[6 empty] | Final library |  |  |  |  | WK 21 |  |  | Number of work weeks (reference) |  |  |  |  | 21.4286 | weeks |  | Vacation |  |  |  |  | 2 days |  | 6+9 Jan 2017
[6 empty] | Official thesis deadline |  |  |  |  | 2017-04-17
[6 empty] | Notenkonferenz |  |  |  |  | 2017-05-16
Presentations
Presentation |  | Date
Intermediate Defense |  | end of december
Final Defense |  | april/may
| Workload [days] |  | Workload [%] |  | October |  |  |  | November | [6 empty] | December | [7 empty] | January | [12 empty] | February |  |  |  |  | March |  |  |  |  | April |  |  |  | May
[5 empty] | 17-21 |  | 24-28 | 31-4 |  | 7-11 |  | 14-18 | 21-25 |  | 28-2 |  | 5-9 | 12-16 | 19-23 |  | 26-30 |  |  |  | 2-6 | 9-13 |  | 16-20 |  | 23-27 | [5 empty] | 30-3 |  | 6-10 | 13-17 | 20-24 | 27-3 |  | 6-10 | 13-17 | 20-24 | 27-31 | 3-7 | 10-14 | 17-21 | 24-28 | 1-5 | 8-12 | 15-19 | 22-26
[5 empty] | 1 |  | 2 | 3 |  | 4 |  | 5 | 6 |  | 7 |  | 8 | 9 | 10 |  | 11 |  |  |  | 12 | 13 |  | 14 |  | 15 | [5 empty] | 16 |  | 17 | 18 | 19 | 20 |  | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
Literature study | [32 empty] | Literature study
User study | [32 empty] | User study
Kinect streaming interface | [32 empty] | Kinect streaming interface
Recording/playback of sensor data | [32 empty] | Recording/playback of sensor data
Base implementation scheme (detection, classification, identification) | [32 empty] | Base implementation scheme
Sensor setup/calibration application | [32 empty] | Sensor setup/calibration application
Anthropomorphic feature detection | [32 empty] | Anthropomorphic feature detection
Probabilistic identification | [32 empty] | Probabilistic identification
Offline identification database | [32 empty] | Offline identification database
Handling of environmental influcences | [32 empty] | Handling of environmental influcences
Demo applications | [32 empty] | Demo applications
Report | [32 empty] | Report
Presentations | [32 empty] | Presentations